## Leveling
BID LEVELING
Bidder → | Voltage Bros Electric | Current Co | Sparky Solutions LLC
SUMMARY
Trade | Electrical | Electrical | Electrical
Bid total | 64300 | 108890 | 77520
Line items | 4 | 5 | 5
Arithmetic flags | 0 | 0 | 0
# exclusions | 3 | 2 | 4
Lowest base bid | ◀ LOW
EXCLUSION MATRIX (filled = this bidder EXCLUDED it → confirm who carries the cost)
Excluded scope | Voltage Bros Electric | Current Co | Sparky Solutions LLC
Fire alarm system | EXCL (p1) |  | EXCL (p1)
Low voltage / data cabling | EXCL (p1) | EXCL (p1) | EXCL (p1)
Temporary power and lighting | EXCL (p1) |  | EXCL (p1)
Equipment/Housekeeping pads |  | EXCL (p1)
Permits |  |  | EXCL (p1)
SCOPE-GAP MATRIX (flagged = likely-missing scope to confirm)
Possible gap | Voltage Bros Electric | Current Co | Sparky Solutions LLC
Main electrical service and distribution beyond panelboards | ⚠
Site lighting and exterior power | ⚠
Specialty systems (e.g., security, access control, AV) | ⚠
Permits, fees, and inspections | ⚠ | ⚠
Coordination drawings (e.g., BIM, clash detection) | ⚠ | ⚠ | ⚠
Testing and commissioning | ⚠
Temporary power and lighting |  | ⚠
Cutting, patching, and core drilling |  | ⚠
Testing and commissioning (beyond basic functionality) |  | ⚠ | ⚠
Demolition of existing electrical systems |  |  | ⚠
Excavation, trenching, and backfill for site lighting conduits |  |  | ⚠
Patching, painting, and finish work after electrical penetrations |  |  | ⚠
Specialized equipment connections (owner furnished, contractor installed) |  |  | ⚠

## Voltage Bros Electric
CSI | Description | Qty | Unit | Unit $ | Amount | Math | Source page
26 05 19 | Branch wiring THHN | 8400 | LF | 1.2 | 10080 | ok | 1
26 51 00 | LED 2x4 troffers | 220 | EA | 145 | 31900 | ok | 1
26 27 26 | Wiring devices + plates | 540 | EA | 18 | 9720 | ok | 1
26 24 16 | Panelboards 42-ckt | 6 | EA | 2100 | 12600 | ok | 1
EXCLUSIONS
(p1) 1. Fire alarm system and devices are EXCLUDED (by others).
(p1) 2. Low voltage / data cabling not included.
(p1) 3. Excludes temporary power and temporary lighting.

## Current Co
CSI | Description | Qty | Unit | Unit $ | Amount | Math | Source page
26 05 19 | Branch circuit wiring | 8400 | LF | 1.35 | 11340 | ok | 1
26 51 00 | LED troffer fixtures 2x4 | 220 | EA | 158 | 34760 | ok | 1
26 27 26 | Devices and coverplates | 540 | EA | 16.5 | 8910 | ok | 1
26 24 16 | Distribution panelboards | 6 | EA | 1980 | 11880 | ok | 1
28 31 00 | Fire alarm system complete | 1 | LS | 42000 | 42000 | ok | 1
EXCLUSIONS
(p1) Low voltage / data cabling by others.
(p1) Excludes equipment pads and housekeeping pads.

## Sparky Solutions LLC
CSI | Description | Qty | Unit | Unit $ | Amount | Math | Source page
26 05 19 | Power branch wiring | 8400 | LF | 1.1 | 9240 | ok | 1
26 51 00 | 2x4 LED troffers | 220 | EA | 139 | 30580 | ok | 1
26 27 26 | Wiring devices | 540 | EA | 15 | 8100 | ok | 1
26 24 16 | Panelboards | 6 | EA | 1850 | 11100 | ok | 1
26 56 00 | Site / exterior lighting | 1 | LS | 18500 | 18500 | ok | 1
EXCLUSIONS
(p1) Fire alarm EXCLUDED.
(p1) Temporary power EXCLUDED.
(p1) Low voltage and data EXCLUDED.
(p1) Permits by GC.